## Read Me
Account Management Tracker · Template
A phased task tracker for everything that needs to happen on a strategic account.
The phase model
Phase I — Foundation
First 30–60 days. SOPs, contact matrix, pricing templates, introductory QBR.
Phase II — Activation
Months 2–4. First shipments, exception handling, initial performance review.
Phase III — Growth
Month 4 onwards. Volume expansion, lane diversification, commercial deepening.
Status values (enforced via dropdown)
• Completed — Task delivered, signed off, no further action
• In Progress — Work has started, owner actively working on it
• Pending — Not yet started — waiting on input, decision, or capacity
• Blocked — Cannot proceed — external dependency, needs escalation
Layout of the Tracker sheet
• Columns A–H: Task list with phase, owner, dates, status, notes
• Columns J–K: Live Status Summary — task counts by status
• Columns O–AD: Phase Calendar — color-coded date ranges per phase
Part of the Logistics Ops Excellence system
github.com/HarshaaNandakumar/logistics-ops-excellence

## Tracker
| ACCOUNT MANAGEMENT TRACKER · [CUSTOMER NAME] | [6 empty] | STATUS SUMMARY |  | PHASE CALENDAR · COLOR-CODED DATE RANGES
# | Phase | Task Name | Owner | Date Started | Date to End | Status | Notes | Total Tasks | 11 | Phase | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13
1 | I | SOP Creation — freight & docs handling | Ops Manager | 2026-01-05 | 2026-01-20 | Completed | Reviewed with customer, signed off | Completed | 5 | Phase I — Foundation
2 | I | Contact Matrix — key stakeholders | KAM | 2026-01-05 | 2026-01-15 | Completed | Published to shared drive | In Progress | 2 | Phase II — Activation
3 | I | Pricing Template — all lanes | Pricing | 2026-01-10 | 2026-01-25 | Completed | Rate card shared, version 1.0 | Pending | 3 | Phase III — Growth
4 | I | Introductory QBR deck | KAM | 2026-01-15 | 2026-02-01 | Completed | QBR held on Feb 2 | Blocked | 1 | Legend: | 2026-01-05: Phase I; 2026-02-09: Phase II; 2026-03-16: Phase III
5 | II | First 10 shipments — close-tracking | Ops Manager | 2026-02-01 | 2026-02-20 | In Progress | 6 of 10 completed without issues
6 | II | DSR format finalization | Analytics | 2026-02-05 | 2026-02-12 | Completed | 25-field template in use
7 | II | Exception handling playbook | Ops Manager | 2026-02-10 | 2026-02-28 | In Progress | Draft under review
8 | II | Month-1 performance review | KAM | 2026-02-25 | 2026-03-05 | Pending
9 | III | Lane expansion scoping — EU routes | KAM | 2026-03-01 | 2026-03-30 | Pending | Awaiting volume commitment
10 | III | Quarterly QBR — Q1 review | KAM | 2026-03-15 | 2026-04-05 | Pending
11 | III | Air freight cross-sell proposal | Pricing | 2026-04-01 | 2026-04-15 | Blocked | Customer decision pending